## Tabelle1
Epic | Task | Sub task | Role | Amount | Size [h] | Scope [h] | Velocity = 65%
FA 1.1 | Processing and Storage of Children's Drawings |  |  |  |  | 0 | 0
WP 1.1.1 |  | Basic dialog for uploading a new, previously unseen drawing | Programmer | 1 | 15 | 15 | 24.75
WP 1.1.2 |  | Curation of the training dataset of drawings | Programmer | 1000 | 0.05 | 50 | 82.5
WP 1.1.3 |  | Experiments with preprocessing of drawings | Programmer | 1 | 10 | 10 | 16.5
WP 1.1.4 |  | Preprocessing pipeline of drawings | Programmer | 1 | 10 | 10 | 16.5
FA 1.2 | Recognition of animals |  |  |  |  | 0 | 0
WP 1.2.1 |  | Experiments with a first CNN for recognizing animals | Programmer | 1 | 5 | 5 | 8.25
WP 1.2.2 |  | CNN for recognizing animals in terms of a multi-class classification | Programmer | 1 | 5 | 5 | 8.25
WP 1.2.3 |  | CNN for recognizing multiple animals in a single drawing | Programmer | 1 | 50 | 50 | 82.5
FA 1.3 | Advanced recognition of animals (optional) |  |  |  |  | 0 | 0
WP 1.3.1 |  | Theoretical consideration of alternative models for animal recognition | Reseacher | 3 | 10 | 30 | 49.5
FA 1.4 | Annotating animals with digits to denote their importance |  |  | 1 |  | 0 | 0
WP 1.4.1 |  | Experiment with digits recognition | Programmer | 1 | 3
WP 1.4.2 |  | Mapping animal and digits with closet distance | Programmer | 1 | 10
FA 1.5 | Annotating animals with markers to denote their relations |  |  |  |  | 0 | 0
WP 1.5.1 |  | Evaluate different marker types and choose the marker type to use | Programmer | 1 | 20 | 20 | 33
FA 1.6 | Annotating animals with activity cards to denote their actions |  |  |  |  | 0 | 0
WP 1.6.1 |  | Sketch and design various activity cards | Graphic designer | 3 | 1 | 3 | 4.95
WP 1.6.2 |  | Experiment with various styles in terms of art | Graphic designer | 3 | 1 | 3 | 4.95
WP 1.6.3 |  | Create the activity cards digitally | Graphic designer | 3 | 1 | 3 | 4.95
WP 1.6.4 |  | Define and make first use of a process for producing physical activity cards | Programmer | 1 | 10 | 10 | 16.5
FA 1.7 | Generating a children's story based on a children's drawing in text form |  | Programmer | 1 | 60 | 60 | 99
FA 1.8 | Telling a previously generated children's story using elegant text-to-speech |  | Programmer | 2 | 20 | 40 | 66
FA 1.9 | Scientific research |  | Reseacher | 40 | 1 | 40 | 66
FA 2.1 | Project evaluation |  |  |  |  | 0 | 0
WP 2.1.1 |  | Preparation of evaluation method |  | 1 | 5 | 5 | 8.25
WP 2.1.2 |  | Evaluation of draw2story |  | 10 | 2 | 20 | 33
WP 2.1.3 |  | Analyzing of evaluation feedback |  | 3 | 3 | 9 | 14.85
Sum | [5 empty] | 354 | 584.1