## Tabelle1
	drawing2story cost plan - estimation of required work hours
#	Functional Area (FA) - Work Package (WP)	Role	Amount	Size [h]	Scope [h]	Velocity = 65%	per Functional Area [h]
FA 1.1	Processing and Storage of Children's Drawings
WP 1.1.1	Basic dialogs	Programmer	3	10	30	49.5
WP 1.1.2	Dataset curation	Programmer	1000	0.025	25	41.25
WP 1.1.3	Experiments with preprocessing / of drawings	Programmer	2	5	10	16.5
WP 1.1.4	Preprocessing pipeline of drawings	Programmer	2	10	20	33
FA 1.2	Recognition of animals					140.25
WP 1.2.1	Experiments with a first CNN	Reseacher	1	10	10	16.5
WP 1.2.2	CNN for recognizing a drawn animal	Programmer	2	20	40	66
WP 1.2.3	CNN for recognizing multiple drawn animals	Programmer	2	20	40	66
FA 1.3	Advanced recognition of animals (optional)					148.5
WP 1.3.1	Theoretical consideration of alternative models	Reseacher	3	5	15	24.75
FA 1.4	Annotating animals with digits to denote their importance					24.75
WP 1.4.1	Model for recognizing a handwritten digit	Reseacher	1	10	10	16.5
WP 1.4.2	Model recognizing multiple handwritten digits	Programmer	2	10	20	33
WP 1.4.3	Associate recognized digits with animals	Programmer	1	20	20	33
FA 1.5	Annotating animals with markers to denote their relations					82.5
WP 1.5.1	Evaluate different marker types	Graphic designer	1	10	10	16.5
WP 1.5.2	Model for recognizing a marker	Reseacher	1	10	10	16.5
WP 1.5.3	Model for recognizing multiple markers	Programmer	2	10	20	33
WP 1.5.4	Associate recognized markers with animals	Programmer	1	20	20	33
WP 1.5.5	Determine groups of animals	Programmer	1	5	5	8.25
FA 1.6	Annotating animals with activity cards to denote their actions					107.25
WP 1.6.1	Sketch and design various activity cards	Graphic designer	7	1	7	11.55
WP 1.6.2	Experiment with various styles in terms of art	Graphic designer	3	1	3	4.95
WP 1.6.3	Create the activity cards digitally	Graphic designer	7	1	7	11.55
WP 1.6.4	Process for producing physical activity cards	Graphic designer	1	10	10	16.5
WP 1.6.5	Model for recognizing activity cards	Programmer	1	10	10	16.5
WP 1.6.6	Model for recognizing multiple activity cards	Programmer	2	10	20	33
WP 1.6.7	Associate recognized activity cards with animals	Programmer	1	20	20	33
FA 1.7	Generating children’s stories					127.05
WP 1.7.1	Create internal data structure to represent an annotated drawing	Programmer	3	5	15	24.75
WP 1.7.2	Experiment with free to integrate LLMs	Reseacher	3	5	15	24.75
WP 1.7.3	Engineer the prompts to make the LLM tell good stories	Programmer	3	5	15	24.75
FA 1.8	Tell children’s story using text to speech					74.25
WP 1.8.1	Apply text-to-speech	Programmer	2	5	10	16.5
FA 1.9	Scientific research					16.5
WP 1.9.1	Placeholder 1 for scientific research	Reseacher	1	10	10	16.5
WP 1.9.2	Placeholder 2 for scientific research	Reseacher	1	10	10	16.5
WP 1.9.3	Placeholder 3 for scientific research	Reseacher	1	10	10	16.5
FA 1.10	Project evaluation					49.5
WP 1.10.1	Preparation of evaluation method	Reseacher	3	5	15	24.75
WP 1.10.1	Evaluation of the product	Reseacher	6	5	30	49.5
WP 1.10.3	Analysis of evaluation feedback	Reseacher	3	5	15	24.75
						99
Total					437	869.55	estimated work hours