## Tabelle1
drawing2story cost plan - estimation of required work hours
# | Functional Area (FA) - Work Package (WP) | Role | Amount | Size [h] | Scope [h] | Velocity = 65% | per Functional Area [h]
FA 1.1 | Processing and Storage of Children's Drawings
WP 1.1.1 | Basic dialogs | Programmer | 3 | 10 | 30 | 49.5
WP 1.1.2 | Dataset curation | Programmer | 1000 | 0.025 | 25 | 41.25
WP 1.1.3 | Experiments with preprocessing of drawings | Programmer | 2 | 5 | 10 | 16.5
WP 1.1.4 | Preprocessing pipeline of drawings | Programmer | 2 | 10 | 20 | 33
FA 1.2 | Recognition of animals | [5 empty] | 140.25
WP 1.2.1 | Experiments with a first CNN | Reseacher | 1 | 10 | 10 | 16.5
WP 1.2.2 | CNN for recognizing a drawn animal | Programmer | 2 | 20 | 40 | 66
WP 1.2.3 | CNN for recognizing multiple drawn animals | Programmer | 2 | 20 | 40 | 66
FA 1.3 | Advanced recognition of animals (optional) | [5 empty] | 148.5
WP 1.3.1 | Theoretical consideration of alternative models | Reseacher | 3 | 5 | 15 | 24.75
FA 1.4 | Annotating animals with digits to denote their importance | [5 empty] | 24.75
WP 1.4.1 | Model for recognizing a handwritten digit | Reseacher | 1 | 10 | 10 | 16.5
WP 1.4.2 | Model recognizing multiple handwritten digits | Programmer | 2 | 10 | 20 | 33
WP 1.4.3 | Associate recognized digits with animals | Programmer | 1 | 20 | 20 | 33
FA 1.5 | Annotating animals with markers to denote their relations | [5 empty] | 82.5
WP 1.5.1 | Evaluate different marker types | Graphic designer | 1 | 10 | 10 | 16.5
WP 1.5.2 | Model for recognizing a marker | Reseacher | 1 | 10 | 10 | 16.5
WP 1.5.3 | Model for recognizing multiple markers | Programmer | 2 | 10 | 20 | 33
WP 1.5.4 | Associate recognized markers with animals | Programmer | 1 | 20 | 20 | 33
WP 1.5.5 | Determine groups of animals | Programmer | 1 | 5 | 5 | 8.25
FA 1.6 | Annotating animals with activity cards to denote their actions | [5 empty] | 107.25
WP 1.6.1 | Sketch and design various activity cards | Graphic designer | 7 | 1 | 7 | 11.55
WP 1.6.2 | Experiment with various styles in terms of art | Graphic designer | 3 | 1 | 3 | 4.95
WP 1.6.3 | Create the activity cards digitally | Graphic designer | 7 | 1 | 7 | 11.55
WP 1.6.4 | Process for producing physical activity cards | Graphic designer | 1 | 10 | 10 | 16.5
WP 1.6.5 | Model for recognizing activity cards | Programmer | 1 | 10 | 10 | 16.5
WP 1.6.6 | Model for recognizing multiple activity cards | Programmer | 2 | 10 | 20 | 33
WP 1.6.7 | Associate recognized activity cards with animals | Programmer | 1 | 20 | 20 | 33
FA 1.7 | Generating children’s stories | [5 empty] | 127.05
WP 1.7.1 | Create internal data structure to represent an annotated drawing | Programmer | 3 | 5 | 15 | 24.75
WP 1.7.2 | Experiment with free to integrate LLMs | Reseacher | 3 | 5 | 15 | 24.75
WP 1.7.3 | Engineer the prompts to make the LLM tell good stories | Programmer | 3 | 5 | 15 | 24.75
FA 1.8 | Tell children’s story using text to speech | [5 empty] | 74.25
WP 1.8.1 | Apply text-to-speech | Programmer | 2 | 5 | 10 | 16.5
FA 1.9 | Scientific research | [5 empty] | 16.5
WP 1.9.1 | Placeholder 1 for scientific research | Reseacher | 1 | 10 | 10 | 16.5
WP 1.9.2 | Placeholder 2 for scientific research | Reseacher | 1 | 10 | 10 | 16.5
WP 1.9.3 | Placeholder 3 for scientific research | Reseacher | 1 | 10 | 10 | 16.5
FA 1.10 | Project evaluation | [5 empty] | 49.5
WP 1.10.1 | Preparation of evaluation method | Reseacher | 3 | 5 | 15 | 24.75
WP 1.10.1 | Evaluation of the product | Reseacher | 6 | 5 | 30 | 49.5
WP 1.10.3 | Analysis of evaluation feedback | Reseacher | 3 | 5 | 15 | 24.75
99
Total |  |  |  |  | 437 | 869.55 | estimated work hours