## drawing2story - cost plan - effort estimation
20231208	drawing2story - cost plan - effort estimation
#	Functional Area (FA) - Work Package (WP)	Role	Amount	Size [h]	Scope [h]	Velocity = 65%	per FA [h]	in days 1d = 8h	per FA [d]
FA 1.1	Processing and Storage of Children's Drawings
WP 1.1.1	Basic dialogs	Programmer	3	8	24	39.6		5.0
WP 1.1.2	Dataset curation	Programmer	1000	0.025	25	41.25		5.2
WP 1.1.3	Experiments with preprocessing / of drawings	Programmer	2	4	8	13.2		1.7
WP 1.1.4	Preprocessing pipeline of drawings	Programmer	2	8	16	26.4		3.3
FA 1.2	Recognition of animals					120.45		15.1
WP 1.2.1	Experiments with a first CNN	Reseacher	1	8	8	13.2		1.7
WP 1.2.2	CNN for recognizing a drawn animal	Programmer	2	16	32	52.8		6.6
WP 1.2.3	CNN for recognizing multiple drawn animals	Programmer	2	16	32	52.8		6.6
FA 1.3	Advanced recognition of animals (optional)					118.8		14.9
WP 1.3.1	Theoretical consideration of alternative models	Reseacher	3	4	12	19.8		2.5
FA 1.4	Annotating animals with digits to denote their importance					19.8		2.5
WP 1.4.1	Model for recognizing a handwritten digit	Reseacher	1	4	4	6.6		0.8
WP 1.4.2	Model recognizing multiple handwritten digits	Programmer	2	4	8	13.2		1.7
WP 1.4.3	Associate recognized digits with animals	Programmer	1	16	16	26.4		3.3
FA 1.5	Annotating animals with markers to denote their relations					46.2		5.8
WP 1.5.1	Evaluate different marker types	Graphic designer	1	4	4	6.6		0.8
WP 1.5.2	Model for recognizing a marker	Reseacher	1	8	8	13.2		1.7
WP 1.5.3	Model for recognizing multiple markers	Programmer	2	8	16	26.4		3.3
WP 1.5.4	Associate recognized markers with animals	Programmer	1	16	16	26.4		3.3
WP 1.5.5	Determine groups of animals	Programmer	1	4	4	6.6		0.8
FA 1.6	Annotating animals with activity cards to denote their actions					79.2		9.9
WP 1.6.1	Sketch and design various activity cards	Graphic designer	8	1	8	13.2		1.7
WP 1.6.2	Experiment with various styles in terms of art	Graphic designer	4	2	8	13.2		1.7
WP 1.6.3	Create the activity cards digitally	Graphic designer	8	2	16	26.4		3.3
WP 1.6.4	Process for producing physical activity cards	Graphic designer	1	8	8	13.2		1.7
WP 1.6.5	Model for recognizing activity cards	Programmer	1	8	8	13.2		1.7
WP 1.6.6	Model for recognizing multiple activity cards	Programmer	2	8	16	26.4		3.3
WP 1.6.7	Associate recognized activity cards with animals	Programmer	1	16	16	26.4		3.3
FA 1.7	Generating children’s stories					132		16.5
WP 1.7.1	Create internal data structure to represent an annotated drawing	Programmer	3	4	12	19.8		2.5
WP 1.7.2	Experiment with free to integrate LLMs	Reseacher	3	4	12	19.8		2.5
WP 1.7.3	Engineer the prompts to make the LLM tell good stories	Programmer	3	4	12	19.8		2.5
FA 1.8	Tell children’s story using text to speech					59.4		7.4
WP 1.8.1	Apply text-to-speech	Programmer	2	4	8	13.2		1.7
FA 1.9	Scientific research					13.2		1.7
WP 1.9.1	Placeholder 1 for scientific research	Reseacher	1	8	8	13.2		1.7
WP 1.9.2	Placeholder 2 for scientific research	Reseacher	1	8	8	13.2		1.7
WP 1.9.3	Placeholder 3 for scientific research	Reseacher	1	8	8	13.2		1.7
FA 1.10	Project evaluation					39.6		5
WP 1.10.1	Preparation of evaluation method	Reseacher	3	4	12	19.8		2.5
WP 1.10.1	Evaluation of the product	Reseacher	6	4	24	39.6		5.0
WP 1.10.3	Analysis of evaluation feedback	Reseacher	3	4	12	19.8		2.5
FA 1.11	Project and Product Management					79.2		9.9
WP 1.11.1	Project Management, Ideation, Solution Design 1	All	3	64	192	316.8		39.6
WP 1.11.2	Project Management, Ideation, Solution Design 2	All	3	16	48	79.2		9.9
WP 1.11.3	Project Management, Ideation, Solution Design 3	All	3	16	48	79.2		9.9
						475.2		59.4
Total					717	1183.05	1183.05	148.7	148.1

	zur Orientierung Total SWS der LV über 3 Semester pro Person
	4 SWS mal 4 (Wochen) mal 4 (Monate) mal 3 (Semester)	192
		mal 3 Personen
	SWS werden nicht ausreichen, um das Projekt fertigzustellen	576