## drawing2story - cost plan - eff
20231208 | drawing2story - cost plan - effort estimation
# | Functional Area (FA) - Work Package (WP) | Role | Amount | Size [h] | Scope [h] | Velocity = 65% | per FA [h] | in days 1d = 8h | per FA [d]
FA 1.1 | Processing and Storage of Children's Drawings
WP 1.1.1 | Basic dialogs | Programmer | 3 | 8 | 24 | 39.6 |  | 5
WP 1.1.2 | Dataset curation | Programmer | 1000 | 0.025 | 25 | 41.25 |  | 5.2
WP 1.1.3 | Experiments with preprocessing of drawings | Programmer | 2 | 4 | 8 | 13.2 |  | 1.7
WP 1.1.4 | Preprocessing pipeline of drawings | Programmer | 2 | 8 | 16 | 26.4 |  | 3.3
FA 1.2 | Recognition of animals | [5 empty] | 120.45 |  | 15.1
WP 1.2.1 | Experiments with a first CNN | Reseacher | 1 | 8 | 8 | 13.2 |  | 1.7
WP 1.2.2 | CNN for recognizing a drawn animal | Programmer | 2 | 16 | 32 | 52.8 |  | 6.6
WP 1.2.3 | CNN for recognizing multiple drawn animals | Programmer | 2 | 16 | 32 | 52.8 |  | 6.6
FA 1.3 | Advanced recognition of animals (optional) | [5 empty] | 118.8 |  | 14.9
WP 1.3.1 | Theoretical consideration of alternative models | Reseacher | 3 | 4 | 12 | 19.8 |  | 2.5
FA 1.4 | Annotating animals with digits to denote their importance | [5 empty] | 19.8 |  | 2.5
WP 1.4.1 | Model for recognizing a handwritten digit | Reseacher | 1 | 4 | 4 | 6.6 |  | 0.8
WP 1.4.2 | Model recognizing multiple handwritten digits | Programmer | 2 | 4 | 8 | 13.2 |  | 1.7
WP 1.4.3 | Associate recognized digits with animals | Programmer | 1 | 16 | 16 | 26.4 |  | 3.3
FA 1.5 | Annotating animals with markers to denote their relations | [5 empty] | 46.2 |  | 5.8
WP 1.5.1 | Evaluate different marker types | Graphic designer | 1 | 4 | 4 | 6.6 |  | 0.8
WP 1.5.2 | Model for recognizing a marker | Reseacher | 1 | 8 | 8 | 13.2 |  | 1.7
WP 1.5.3 | Model for recognizing multiple markers | Programmer | 2 | 8 | 16 | 26.4 |  | 3.3
WP 1.5.4 | Associate recognized markers with animals | Programmer | 1 | 16 | 16 | 26.4 |  | 3.3
WP 1.5.5 | Determine groups of animals | Programmer | 1 | 4 | 4 | 6.6 |  | 0.8
FA 1.6 | Annotating animals with activity cards to denote their actions | [5 empty] | 79.2 |  | 9.9
WP 1.6.1 | Sketch and design various activity cards | Graphic designer | 8 | 1 | 8 | 13.2 |  | 1.7
WP 1.6.2 | Experiment with various styles in terms of art | Graphic designer | 4 | 2 | 8 | 13.2 |  | 1.7
WP 1.6.3 | Create the activity cards digitally | Graphic designer | 8 | 2 | 16 | 26.4 |  | 3.3
WP 1.6.4 | Process for producing physical activity cards | Graphic designer | 1 | 8 | 8 | 13.2 |  | 1.7
WP 1.6.5 | Model for recognizing activity cards | Programmer | 1 | 8 | 8 | 13.2 |  | 1.7
WP 1.6.6 | Model for recognizing multiple activity cards | Programmer | 2 | 8 | 16 | 26.4 |  | 3.3
WP 1.6.7 | Associate recognized activity cards with animals | Programmer | 1 | 16 | 16 | 26.4 |  | 3.3
FA 1.7 | Generating children’s stories | [5 empty] | 132 |  | 16.5
WP 1.7.1 | Create internal data structure to represent an annotated drawing | Programmer | 3 | 4 | 12 | 19.8 |  | 2.5
WP 1.7.2 | Experiment with free to integrate LLMs | Reseacher | 3 | 4 | 12 | 19.8 |  | 2.5
WP 1.7.3 | Engineer the prompts to make the LLM tell good stories | Programmer | 3 | 4 | 12 | 19.8 |  | 2.5
FA 1.8 | Tell children’s story using text to speech | [5 empty] | 59.4 |  | 7.4
WP 1.8.1 | Apply text-to-speech | Programmer | 2 | 4 | 8 | 13.2 |  | 1.7
FA 1.9 | Scientific research | [5 empty] | 13.2 |  | 1.7
WP 1.9.1 | Placeholder 1 for scientific research | Reseacher | 1 | 8 | 8 | 13.2 |  | 1.7
WP 1.9.2 | Placeholder 2 for scientific research | Reseacher | 1 | 8 | 8 | 13.2 |  | 1.7
WP 1.9.3 | Placeholder 3 for scientific research | Reseacher | 1 | 8 | 8 | 13.2 |  | 1.7
FA 1.10 | Project evaluation | [5 empty] | 39.6 |  | 5
WP 1.10.1 | Preparation of evaluation method | Reseacher | 3 | 4 | 12 | 19.8 |  | 2.5
WP 1.10.1 | Evaluation of the product | Reseacher | 6 | 4 | 24 | 39.6 |  | 5
WP 1.10.3 | Analysis of evaluation feedback | Reseacher | 3 | 4 | 12 | 19.8 |  | 2.5
FA 1.11 | Project and Product Management | [5 empty] | 79.2 |  | 9.9
WP 1.11.1 | Project Management, Ideation, Solution Design 1 | All | 3 | 64 | 192 | 316.8 |  | 39.6
WP 1.11.2 | Project Management, Ideation, Solution Design 2 | All | 3 | 16 | 48 | 79.2 |  | 9.9
WP 1.11.3 | Project Management, Ideation, Solution Design 3 | All | 3 | 16 | 48 | 79.2 |  | 9.9
[7 empty] | 475.2 |  | 59.4
Total |  |  |  |  | 717 | 1183.05 | 1183.05 | 148.7 | 148.1
zur Orientierung Total SWS der LV über 3 Semester pro Person
| 4 SWS mal 4 (Wochen) mal 4 (Monate) mal 3 (Semester) | 192
mal 3 Personen
| SWS werden nicht ausreichen, um das Projekt fertigzustellen | 576